## Expertly To-Do List
Section | Nature | Task | Owner | Status
Overall | Backend UI/UX | Mobile View - Review of all pages independently | Shreyans | Not Started
Admin Dashboard | Operational | Finalize payment process (escrow / IPO mandate / refund process) | Mukesh | Not Started
Admin Dashboard | Backend UI/UX | Fixing LinkedIn import & submit page | Shreyans | Not Started
Admin Dashboard | UI/UX | Add application rejection remarks (Approved / Rejected / Resubmission) | Roshan | Not Started
Admin Dashboard | UI/UX | Set renewal policy (based on membership date) | Roshan | Not Started
Admin Dashboard | Operational | Build user directory (user data, subscribers, member renewals) | Roshan | Not Started
Admin Dashboard | Operational | Resolve domain / auto-mail spam concern | Team | Not Started
Members Profile & Dashboard | Backend UI/UX | Add Edit button and Verified button on Members Profile page wherever needed | Roshan/Shreyans | Not Started
Members Profile & Dashboard | UI/UX | Set login fields -> First Name, Last Name, City | Roshan | Not Started
Members Profile & Dashboard | UI/UX | Add members registration numbers (Bar Council No. / CA membership) as verification process | Roshan | Not Started
Members Profile & Dashboard | UI/UX | Define single verification process to increase credibility (define 'how we vet') | Roshan | Not Started
Members Profile & Dashboard | Backend UI/UX | Restrict access to member details (limited visibility) | Shreyans | Not Started
Members Profile & Dashboard | Backend UI/UX | Provide option to disable details preview, if needed for members | Shreyans | Not Started
Website Review & Fixes | UI/UX | Review entire website for gaps, issues, functional bugs, etc. | Ankita | In Progress
Website Review & Fixes | UI/UX | Fix hover-on-calendar mixed/cut display bug | Mukesh | Done
Website Review & Fixes | UI/UX | Import data / port change -> add 'back to top' / side scroll | Roshan | Not Started
Website Review & Fixes | Backend UI/UX | Fix footer | Shreyans | Not Started
Website Review & Fixes | UI/UX | Remove 'quick link' and shift critical points | Mukesh | Done
SEO / AEO | Applicational | Make immediate SEO changes to website | Roshan | Not Started
SEO / AEO | Applicational | Work on SEO from all perspectives | Roshan | Not Started
SEO / AEO | Applicational | Align objective: SEO + AEO without compromising interactions | Team | Not Started
SEO / AEO | Applicational | Explore visit-based restriction for SEO Expert content | Team | Not Started
Articles & Content | Applicational | Write at least 50-100 articles | Ankita & Roshan | Not Started
Articles & Content | UI/UX | Add easy topic-suggestion bar for articles | Roshan | Not Started
Articles & Content | UI/UX | Add AI Summary / Expertly Summary for articles | Roshan | Not Started
Articles & Content | UI/UX | Move 'share' feature to end of article | Mukesh | Done
Articles & Content | UI/UX | Decide whether to add FAQ section | Team | Not Started
Articles & Content | UI/UX | Fix: clicking article should redirect to actual article | Mukesh | Done
Articles & Content | Applicational | Decide whether articles should be freely accessible | Team | Not Started
Articles & Content | Backend UI/UX | Add article engagement insights for members + comments for discussion | Roshan | Not Started
Articles & Content | UI/UX | Change visual for practice area (category box classification) | Roshan | Not Started
Articles & Content | UI/UX | Change practice area picture | Roshan | Not Started
Events & Calendar | Applicational | Build AI bots to collect event details across the world | Roshan | Not Started
Events & Calendar | UI/UX | Fix calendars | Mukesh | Done
Members Profile & Dashboard | UI/UX | Include time preference in consultation request | Roshan | Not Started
Members Profile & Dashboard | UI/UX | Handle 'couldn't find expert in that league' -> drop requirement, allow referral input OR Add hot category section | Roshan | Not Started
Mail / Notifications | Applicational | Decide mail frequency: weekly or daily | Team | Not Started
Mail / Notifications | Applicational | Decide mail content: summary or full | Team | Not Started
Mail / Notifications | Applicational | Decide mail generation: AI-generated or self-written | Team | Not Started
Partnerships & Launch | Operational | Reach out to launch partners (Peers?) | Mukesh | Not Started
New Pages / Site Structure | UI/UX | Add feedback/experience dropbox or 'deal closed' section | Roshan | Not Started
New Pages / Site Structure | UI/UX | Create 'How it Works' page (Search -> Match -> Consult -> chat/platform) | Roshan | Not Started
Overall Strategy / Operational | Operational | Finalize overall strategy -> MVP -> subpage | Mukesh | Not Started
Overall Strategy / Operational | Operational | Pricing discussion | Mukesh | Not Started
Overall Strategy / Operational | Operational | Define operational items (broad framework, MVP + future requirements) | Mukesh | Not Started
Overall Strategy / Operational | Operational | Figure backend for peerconnect - AI/calling facility (Zoom/teams/meet) | Shreyans/Mukesh | Not Started
Overall Strategy / Operational | Operational | Explore patenting the work | Mukesh | Not Started
Overall Strategy / Operational | Operational | Explore Fintech Fest participation | Mukesh | Not Started

## Admin dashboard
Section | Section | Task | Owner | Status
Admin Dashboard | Overview | Dashboard to reflect: no. of refunds outstanding | Roshan | Done
Admin Dashboard | Overview | Dashboard to reflect: memberships expiring due this week/month (SLA age) | Roshan | Done
Admin Dashboard | Overview | How and where are dropouts tracked. We might need a conversion funnel view | Roshan | Done
Admin Dashboard | Overview | Enable conversion funnel view: Viewed/Visited > Applied > Payment Initiated > Converted | Roshan | Done
Admin Dashboard | Applications | Decide if Ref ID is needed | Roshan/team | Done
Admin Dashboard | Applications | Add verification stage tracking (Credentials, Testimonial review, xyz) | Roshan | Done
Admin Dashboard | Applications | Add remarks field for applications - whether it's for rejection, resubmission or in general | Roshan | Done
Admin Dashboard | Applications | add payment status (Collected/Refunded/Failed) | Roshan | Done
Admin Dashboard | Applications | Decide whether summarized/tabulated data should have filters | Roshan | Done
Admin Dashboard | Applications | Add Reviewer column under Applications (since manually handled, for who's incharge & stocktake) | Roshan | Done
Admin Dashboard | Articles | Add disclaimer on AI articles - AI-generated & approved by editor team | Roshan | Done
Admin Dashboard | Articles | Logic check: Why cover image is requested as a URL not jpg/png? | Roshan | Done
Admin Dashboard | Articles | Decide: allow only one practice area, or add a topic option instead of practice area | Roshan | Done
Admin Dashboard | Members | Show membership detail in member directory | Roshan | Done
Admin Dashboard | Members | Show profile completion % in member directory | Roshan | Done
Admin Dashboard | Members | Show payment status (for upcoming) in member directory | Roshan | Done
Admin Dashboard | Members | Colums to be added: verified status + view, period due, and contribution (1A/3C/4R) | Roshan | Discuss
Admin Dashboard | Members | Profile edit- There's some issue - to check & fix | Roshan | Done
Admin Dashboard | Members | Decide whether to provide transcript download option (member dashboard) | Roshan | Done
Admin Dashboard | Consultation Requests | Build consultation request tracking table: Date/#, Requester, Requestee, Request, Sent, Revert | Roshan | Done
Admin Dashboard | Consultation Requests | Decide on call/mail option next to members (for our internal ease of action) | Roshan | Done
Admin Dashboard | Events | Fix date format (all caps) | Roshan | Done
Admin Dashboard | Events | Add event category: Fintech, Law, Startup | Roshan | Done
Admin Dashboard | Events | Add organiser details to events | Roshan | Done
Admin Dashboard | Events | Add RSVP/Registration link (URL) to events | Roshan | Done
Admin Dashboard | Events | Decide if recommender's name should be collated when events are recommended | Mukesh/Team | Not Started
Operational | Events | Explore collaboration with event partners - discounts/perks for members | Mukesh/Team | Not Started
Operational | Events | Display sponsored events as promo banners (revenue & recognition outlet) | Mukesh/Team | Not Started
Operational | Events | Decide on individual calendar page if 3rd-party calendar integration isn't possible | Mukesh/Team | Not Started
Operational | Overall | Clarify where user info is displayed | Mukesh/Team | Not Started
Operational | Overall | How will we track active users/DUD users? Add dormant account tracking | Mukesh/Team
Trust & Safety |  | Decide if we need a customer support bot/ticket system | Mukesh/Team | Not Started
Trust & Safety |  | Define how copyright/plagiarism flags will be tackled | Mukesh/Team | Not Started
Trust & Safety |  | Decide if members can report an account | Mukesh/Team | Not Started
Trust & Safety |  | Add verification checkpoint for data beyond application point (currently visible only once; add one more trackpoint) As in for newly fed data, if the same has been verified there's no check point | Roshan | Not Started
Payments & Reconciliation |  | Build reconciliation system between payment gateway, wallet & bank records | Shreyans | Not Started
Payments & Reconciliation |  | Decide: charge upfront, refund on rejection (may cost gateway fee, as non-refundable) | Mukesh | Not Started
Payments & Reconciliation |  | Track refund/cancellation volume & turnaround time; should we have separate billing dashboard, showing revenue summary? | Roshan | Not Started
Payments & Reconciliation |  | Finalize pricing - GST treatment + cross-border transaction implications | Mukesh | Not Started